## Risk Analysis and Management Ta
Risk ID | Risk Description | Impact (High/Med/Low) | Likelihood (High/Med/Low) | Mitigation Plan | Contingency Plan
1 | Delay in project planning | High | Medium | Schedule extra buffer time for planning tasks. | Reallocate resources to expedite planning.
2 | Technical challenges in development | High | High | Conduct regular code reviews and testing. | Engage external consultants if needed.
3 | Resource availability issues | Medium | Medium | Cross-train team members to handle multiple roles. | Outsource specific tasks to freelancers.
4 | Budget overruns | High | Medium | Monitor expenses weekly and reduce waste. | Request additional funding approval.
5 | Integration failures with APIs | Medium | High | Test API integrations early and often. | Use mock APIs or alternate solutions.
6 | Security vulnerabilities | High | Medium | Perform penetration testing and code audits. | Rollback changes and secure backup systems.
7 | Delayed user feedback | Low | Medium | Engage stakeholders early in the process. | Use internal team reviews for interim feedback.
8 | Hardware or cloud infrastructure failure | High | Low | Use redundant systems and cloud backup. | Shift workloads to alternate systems.