## Sheet1
WBS | Task | Labor Hrs | Rate | Materials Units | $/Unit | Fixed Costs | Budget | Actual | Under(Over)
1 | [Project Planning]
1.1 | Requirement Gathering | 8 | 50 | 0 | 0 | 100 | 500
1.2 | Define Project Scope | 10 | 50 | 0 | 0 | 200 | 700
2 | [Risk Analysis]
2.1 | Identify Potential Risks | 6 | 60 | 0 | 0 | 0 | 360
3 | [Design Phase]
3.1 | Create Wireframes | 15 | 40 | 10 | 10 | 500 | 1300
4 | [Development Phase]
4.1 | Set Up Backend Architecture | 20 | 45 | 15 | 25 | 1000 | 2875
4.2 | Develop Frontend | 25 | 45 | 20 | 30 | 2000 | 3875
5 | [Testing and QA]
5.1 | Perform Functional Testing | 12 | 50 | 5 | 15 | 500 | 1160