## Task_Table1
ID | Indicators | Task_Mode | Task_Name | Duration | Start_Date | Finish_Date | Predecessors | Resource_Names
1 |  | Manually Scheduled | ShopVista | 115 days | 2024 December 01 8:00 AM | 2025 May 08 5:00 PM
2 |  | Manually Scheduled | Project Planning | 14 days | 2024 December 01 8:00 AM | 2024 December 18 5:00 PM
3 |  | Manually Scheduled | Requirement gathering | 2 days | 2024 December 01 8:00 AM | 2024 December 02 5:00 PM
4 |  | Manually Scheduled | Define project scope | 2 days | 2024 December 03 8:00 AM | 2024 December 04 5:00 PM | 3
5 |  | Manually Scheduled | Identify stakeholders | 1 day | 2024 December 01 8:00 AM | 2024 December 01 5:00 PM
6 |  | Manually Scheduled | Approve project charter | 1 day | 2024 December 05 8:00 AM | 2024 December 05 5:00 PM | 4,5
7 |  | Manually Scheduled | Project Charter Approved | 0 days | 2024 December 06 8:00 AM | 2024 December 06 8:00 AM | 6
8 |  | Manually Scheduled | Conduct stakeholder interviews | 2 days | 2024 December 06 8:00 AM | 2024 December 09 5:00 PM | 6
9 |  | Manually Scheduled | Define project objectives | 1 day | 2024 December 10 8:00 AM | 2024 December 10 5:00 PM | 8
10 |  | Manually Scheduled | Develop communication plan | 1 day | 2024 December 01 8:00 AM | 2024 December 01 5:00 PM
11 |  | Manually Scheduled | Assign team roles and responsibilities | 2 days | 2024 December 02 8:00 AM | 2024 December 03 5:00 PM | 10
12 |  | Manually Scheduled | Identify resource requirements | 1 day | 2024 December 11 8:00 AM | 2024 December 11 5:00 PM | 9
13 |  | Manually Scheduled | Develop project timeline | 1 day | 2024 December 12 8:00 AM | 2024 December 12 5:00 PM | 12
14 |  | Manually Scheduled | Review and approve project risk register | 0 days | 2024 December 01 8:00 AM | 2024 December 01 8:00 AM
15 |  | Manually Scheduled | Risk Analysis | 14 days | 2024 December 01 8:00 AM | 2024 December 18 5:00 PM
16 |  | Manually Scheduled | Identify potential risks to scope, schedule, and budget | 2 days | 2024 December 01 8:00 AM | 2024 December 02 5:00 PM
17 |  | Manually Scheduled | Develop mitigation strategies for identified risks | 2 days | 2024 December 03 8:00 AM | 2024 December 04 5:00 PM | 16
18 |  | Manually Scheduled | Create risk management documentation | 1 day | 2024 December 05 8:00 AM | 2024 December 05 5:00 PM | 17
19 |  | Manually Scheduled | Risk Management Plan Approved | 0 days | 2024 December 06 8:00 AM | 2024 December 06 8:00 AM | 18
20 |  | Manually Scheduled | Assess technology stack obsolescence risks | 2 days | 2024 December 01 8:00 AM | 2024 December 02 5:00 PM
21 |  | Manually Scheduled | Evaluate third-party integration risks | 1 day | 2024 December 03 8:00 AM | 2024 December 03 5:00 PM | 20
22 |  | Manually Scheduled | Develop contingency plans for critical risks | 1 day | 2024 December 04 8:00 AM | 2024 December 04 5:00 PM | 21
23 |  | Manually Scheduled | Conduct regular risk review meetings with stakeholders | 1 day | 2024 December 01 8:00 AM | 2024 December 01 5:00 PM
24 |  | Manually Scheduled | Design Phase | 16 days | 2024 December 01 8:00 AM | 2024 December 20 5:00 PM
25 |  | Manually Scheduled | Functional Design | 6 days | 2024 December 01 8:00 AM | 2024 December 06 5:00 PM
26 |  | Manually Scheduled | Create wireframes for user interface | 2 days | 2024 December 02 8:00 AM | 2024 December 03 5:00 PM | 23
27 |  | Manually Scheduled | Define user roles and permissions | 1 day | 2024 December 04 8:00 AM | 2024 December 04 5:00 PM | 26
28 |  | Manually Scheduled | Map user flows for e-commerce operations | 2 days | 2024 December 05 8:00 AM | 2024 December 06 5:00 PM | 27
29 |  | Manually Scheduled | Plan security measures
30 |  | Manually Scheduled | Technical Design | 6 days | 2024 December 01 8:00 AM | 2024 December 06 5:00 PM
31 |  | Manually Scheduled | Design database schema for product and user data | 2 days | 2024 December 01 8:00 AM | 2024 December 02 5:00 PM
32 |  | Manually Scheduled | Define API architecture for third-party integrations | 2 days | 2024 December 03 8:00 AM | 2024 December 04 5:00 PM | 31
33 |  | Manually Scheduled | Optimize database schema for scalability and performance | 2 days | 2024 December 03 8:00 AM | 2024 December 04 5:00 PM | 31
34 |  | Manually Scheduled | Visual Design | 4 days | 2024 December 01 8:00 AM | 2024 December 04 5:00 PM
35 |  | Manually Scheduled | Create style guide for user interface | 1 day | 2024 December 01 8:00 AM | 2024 December 01 5:00 PM
36 |  | Manually Scheduled | Design mobile-first layouts for responsive web design | 2 days | 2024 December 02 8:00 AM | 2024 December 03 5:00 PM | 35
37 |  | Manually Scheduled | Develop prototype mockups for feedback | 1 day | 2024 December 04 8:00 AM | 2024 December 04 5:00 PM | 36
38 |  | Manually Scheduled | Design Phase Complete | 0 days | 2024 December 04 8:00 AM | 2024 December 04 8:00 AM | 36
39 |  | Manually Scheduled | Development Phase | 40 days | 2024 December 01 8:00 AM | 2025 January 23 5:00 PM
40 |  | Manually Scheduled | Backend Development | 20 days | 2024 December 01 8:00 AM | 2024 December 26 5:00 PM
41 |  | Manually Scheduled | Set up backend architecture | 5 days | 2024 December 01 8:00 AM | 2024 December 05 5:00 PM
42 |  | Manually Scheduled | Develop product management system | 7 days | 2024 December 06 8:00 AM | 2024 December 16 5:00 PM | 41
43 |  | Manually Scheduled | Implement vendor management features | 5 days | 2024 December 17 8:00 AM | 2024 December 23 5:00 PM | 41
44 |  | Manually Scheduled | Build APIs for payment gateways | 3 days | 2024 December 06 8:00 AM | 2024 December 10 5:00 PM | 41
45 |  | Manually Scheduled | Backend Development Complete | 0 days | 2024 December 11 8:00 AM | 2024 December 11 8:00 AM | 44
46 |  | Manually Scheduled | Frontend Development | 15 days | 2024 December 01 8:00 AM | 2024 December 19 5:00 PM
47 |  | Manually Scheduled | Create a customer-facing storefront | 6 days | 2024 December 06 8:00 AM | 2024 December 13 5:00 PM | 41
48 |  | Manually Scheduled | Build a vendor dashboard for product management | 6 days | 2024 December 11 8:00 AM | 2024 December 18 5:00 PM | 44
49 |  | Manually Scheduled | Integrate a shopping cart and checkout system | 3 days | 2024 December 11 8:00 AM | 2024 December 13 5:00 PM | 44
50 |  | Manually Scheduled | Frontend Development Complete | 0 days | 2024 December 16 8:00 AM | 2024 December 16 8:00 AM | 49
51 |  | Manually Scheduled | Additional Features | 10 days | 2024 December 01 8:00 AM | 2024 December 12 5:00 PM
52 |  | Manually Scheduled | Develop customer review and rating system | 3 days | 2024 December 01 8:00 AM | 2024 December 03 5:00 PM
53 |  | Manually Scheduled | Implement search functionality with filters | 3 days | 2024 December 04 8:00 AM | 2024 December 06 5:00 PM | 52
54 |  | Manually Scheduled | Add multilingual and multi-currency support | 4 days | 2024 December 09 8:00 AM | 2024 December 12 5:00 PM | 53
55 |  | Manually Scheduled | Security Implementation | 6 days | 2024 December 01 8:00 AM | 2024 December 06 5:00 PM
56 |  | Manually Scheduled | Configure HTTPS and SSL certificates | 1 day | 2024 December 01 8:00 AM | 2024 December 01 5:00 PM
57 |  | Manually Scheduled | Implement role-based access control (RBAC) | 2 days | 2024 December 02 8:00 AM | 2024 December 03 5:00 PM | 56
58 |  | Manually Scheduled | Add input validation to prevent SQL injection | 3 days | 2024 December 04 8:00 AM | 2024 December 06 5:00 PM | 57
59 |  | Manually Scheduled | Testing and QA | 15 days | 2024 December 01 8:00 AM | 2024 December 19 5:00 PM
60 |  | Manually Scheduled | Perform unit testing for backend modules | 3 days | 2024 December 04 8:00 AM | 2024 December 06 5:00 PM | 52
61 |  | Manually Scheduled | Conduct UI/UX testing for the user interface | 3 days | 2024 December 16 8:00 AM | 2024 December 18 5:00 PM | 47
62 |  | Manually Scheduled | Execute integration testing for APIs and third-party services | 3 days | 2024 December 06 8:00 AM | 2024 December 10 5:00 PM | 41
63 |  | Manually Scheduled | Perform stress testing under high traffic conditions | 3 days | 2024 December 09 8:00 AM | 2024 December 11 5:00 PM | 55
64 |  | Manually Scheduled | Conduct end-to-end testing of the checkout process | 3 days | 2024 December 09 8:00 AM | 2024 December 11 5:00 PM | 55
65 |  | Manually Scheduled | Validate data encryption and secure storage protocols | 2 days | 2024 December 09 8:00 AM | 2024 December 10 5:00 PM | 55
66 |  | Manually Scheduled | Perform user acceptance testing (UAT) with beta users | 3 days | 2024 December 09 8:00 AM | 2024 December 11 5:00 PM | 60
67 |  | Manually Scheduled | Testing Phase Complete | 0 days | 2024 December 12 8:00 AM | 2024 December 12 8:00 AM | 66
68 |  | Manually Scheduled | Deployment and Maintenance | 10 days | 2024 December 01 8:00 AM | 2024 December 12 5:00 PM
69 |  | Manually Scheduled | Set up production environment on cloud (AWS for example ) | 2 days | 2024 December 01 8:00 AM | 2024 December 02 5:00 PM
70 |  | Manually Scheduled | Configure DNS and hosting settings | 1 day | 2024 December 03 8:00 AM | 2024 December 03 5:00 PM | 69
71 |  | Manually Scheduled | Deploy staging environment for pre-launch testing | 2 days | 2024 December 01 8:00 AM | 2024 December 02 5:00 PM
72 |  | Manually Scheduled | Migrate staging database to production | 1 day | 2024 December 03 8:00 AM | 2024 December 03 5:00 PM | 71
73 |  | Manually Scheduled | Conduct post-deployment verification tests | 2 days | 2024 December 04 8:00 AM | 2024 December 05 5:00 PM | 72
74 |  | Manually Scheduled | System Deployed to Production | 0 days | 2024 December 06 8:00 AM | 2024 December 06 8:00 AM | 73
75 |  | Manually Scheduled | Monitor uptime and performance metrics | 1 day | 2024 December 03 8:00 AM | 2024 December 03 5:00 PM | 69
76 |  | Manually Scheduled | Prepare end-user documentation and FAQs | 1 day | 2024 December 03 8:00 AM | 2024 December 03 5:00 PM | 71
77 |  | Manually Scheduled | Unique Features | 10 days | 2024 December 01 8:00 AM | 2024 December 12 5:00 PM
78 |  | Manually Scheduled | Build predictive analytics dashboard for sales trends | 3 days | 2024 December 04 8:00 AM | 2024 December 06 5:00 PM | 76
79 |  | Manually Scheduled | Develop AI-powered chatbot for customer support | 3 days | 2024 December 04 8:00 AM | 2024 December 06 5:00 PM | 76
80 |  | Manually Scheduled | Implement gamification features for customer retention | 2 days | 2024 December 09 8:00 AM | 2024 December 10 5:00 PM | 78
81 |  | Manually Scheduled | Add voice search functionality for product search | 1 day | 2024 December 09 8:00 AM | 2024 December 09 5:00 PM | 78
82 |  | Manually Scheduled | AI Features Implemented | 0 days | 2024 December 10 8:00 AM | 2024 December 10 8:00 AM | 81
83 |  | Manually Scheduled | Introduce AR product previews for better user experience | 1 day | 2024 December 09 8:00 AM | 2024 December 09 5:00 PM | 79
84 |  | Manually Scheduled | Enable loyalty rewards and discount codes | 1 day | 2024 December 09 8:00 AM | 2024 December 09 5:00 PM | 78
85 |  | Manually Scheduled | Closing | 5 days | 2024 December 18 8:00 AM | 2024 December 24 5:00 PM
86 |  | Manually Scheduled | Prepare final project report | 2 days | 2024 December 13 8:00 AM | 2024 December 16 5:00 PM | 77
87 |  | Manually Scheduled | Create a lessons-learned document | 1 day | 2024 December 13 8:00 AM | 2024 December 13 5:00 PM | 77
88 |  | Manually Scheduled | Present the project to stakeholders for approval | 1 day | 2024 December 13 8:00 AM | 2024 December 13 5:00 PM | 77
89 |  | Manually Scheduled | Archive project documentation and code repository | 1 day | 2024 December 13 8:00 AM | 2024 December 13 5:00 PM | 77
90 |  | Manually Scheduled | Project Closure Complete | 0 days | 2024 December 16 8:00 AM | 2024 December 16 8:00 AM | 89